## Sheet1
Review |  | Permit or Study Name | Agency/ Dept. | Data Needed | Schedule Date to be Submitted To Agency | Schedule Date for Agency Approval | Comments
Environmental permits
SOUTH DAKOTA | Pennington County | Floodplain Development Permit | Pennington County Planning Dept. | Final design. |  |  | Likely all floodplains will be spanned. If not, floodplain survey would be required. Permit turnaround time is 7-14 days.
WYOMING |  | WYPDES Large Construction General Permit \ SWPPP | WY Dept of Environmental Quality | Final design | 2014-11-15 | 2014-12-15 | The Stormwater NOI and SWPPP must be submitted to WYDEQ a minimum of 30 days prior to construction.
|  | Section 401, Water Quality Certification | WY Dept of Environmental Quality, Water Division | Final design | 2014-11-01 | 2014-12-01 | 401 Water Quality certification is granted with the issuance of the 404 permit. No application necessary.
|  | State Lands Survey Permit and Easement | Office of State Lands and Investments | Final design | 2014-10-01 | 2014-11-01 | Survey permits have been acquired.
SOUTH DAKOTA |  | Section 401, Water Quality Certification | South Dakota Department of Environment and Natural Resources (DENR) | Final design. | 2014-11-01 | 2014-12-01 | 401 Water Quality certification is granted with the issuance of the 404 permit. No application necessary.
|  | NPDES General Permit for Storm Water Discharges from Construction Activities | South Dakota Department of Environment and Natural Resources (DENR) | Final Design. Preparation of a SWPPP | Minimum of 15 days prior to construction | Prior to construction | The Stormwater NOI must be submitted a minimum of 15 days prior to construction. A SWPPP must be in place prior to construction.
FEDERAL REVIEW |  | U.S. Army Corps of Engineers Section 404 Permit- Nationwide Permit #12 | U.S. Army Corps of Engineers | Final design. | 2014-11-01 | 2014-12-01 | The project will likely require a Nationwide Permit #12
|  | Right-of-Way Permit | Bureau of Land Management |  | In process | 2014-12-15 | NEPA
|  | Special Use Permit | US Forest Service |  | In process | 2014-12-15 | NEPA
Non-Environmental Permits
SOUTH DAKOTA | Pennington County | Permit to Occupy ROW | Pennington County Highway Department | Final design | 2014-12-01 | 2014-12-15 | 7-14 day permit turnaround
|  | Temporary Approach Permit/Notification | Pennington County Highway Department | Final design |  |  | Thomas Wilsey, Superintendant, is not sure such a permit exists but would like a notification and drawings of any approaches.
|  | Utility Installation Permit | Pennington County Highway Department | Final design | 2014-12-01 | 2014-12-15 | 7-14 day permit turnaround
|  | Building Permit | Pennington County Planning Dept. |  | Project description submitted 9/10/2014 |  | PJ Conover, interim Director would like to see a project description to determine if a Building Permit is required. If required, permit turnaround is 7-10 days.
|  | Construction Permit | Pennington County Planning Dept. |  | Project description submitted 9/10/2014 |  | PJ Conover, interim Director would like to see a project description to determine if a Construction Permit is required. If required, permit turnaround is 7-10 days.
WYOMING |  | WYDOT Form M54 | Wyoming Department of Transportation | Final design | 2014-11-01 | 2014-12-01 | Typical turnaround is 1-4 weeks. They prefer 11x17 drawings.
SOUTH DAKOTA |  | Utility Permit | South Dakota Department of Transportation | Final design | 2014-11-15 | 2014-12-01 | Typical turnaround is 1-2 weeks.
RAILROAD REVIEW |  | Wire and Cable Installation Permit | Railroad | Final design | 2014-11-15 | 2015-01-14 | BHP
|  | Right-of-Entry for Access to Railroad Properties | Railroad | Final design | 2014-11-15 | 2015-01-14 | BHP